## Defect Report
Project Name |  | CTS
TC Created by |  | Habeeb Almseideen
TC Reviewed by |  | Mohammad Rawass
Defect Report
ID | Priority | Description | URL | Submit Date | Reported By | Environment | Steps to reproduce | Expected Result | Actual result | Severity | Assigned to | Status
TC-DC-01 | High | Accessing a page without logging in is not prompting for login. The problem related to authentication checks not being properly implemented. | /goToAddStudent | 15/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser. 2. Navigate to the URL 3. Observe that the page is accessible without being prompted for login. | Redirect to LogIn Page /login | Page was accessible | Major | Habeeb Almseideen | Resolved
TC-DC-02 | Low | When accessing the website, the font or text type in the navbar is not loading as expected. This issue affects the visual appearance and readability of the navigation bar. | All | 15/12/2023 | Mohammad Rawass | PC Windows 11 Microsoft Edge (10.91) | 1. Open a Edge browser. 2. Navigate to any URL 3. Observe the font or text type in the navbar. | The font or text type in the navbar should load correctly, maintaining the intended visual style. | The font or text type in the navbar is not loading as expected, resulting in a visual discrepancy. | Minor | Habeeb Almseideen | Open
TC-DC-03 | Low | When accessing the website, the font or text type in the navbar is not loading as expected. This issue affects the visual appearance and readability of the navigation bar. | All | 15/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser. 2. Navigate to any URL 3. Observe the font or text type in the navbar. | The font or text type in the navbar should load correctly, maintaining the intended visual style. | The font or text type in the navbar is not loading as expected, resulting in a visual discrepancy. | Minor | Habeeb Almseideen | Resolved
TC-DC-04 | Medium | When trying to enter the password in the sign up page the max limit validation is not activated | /register | 16/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. fill the required input area. 4.Write the password with more than the max limit (31). 5.Observe that after pressing register button will redirect you to the login page. | Validation message that informs the user to keep the password in the limit of 51 digits | After filling the required inputs and pressing the registration button it will redirect you to the login page as if it was a successful registration which is false because trying to login will fail because user registration wasn't saved to the database | Major | Habeeb Almseideen | Resolved
TC-DC-05 | Medium | When trying to enter the first and last Name in the sign up page the Validation is not working for the integer input | /register | 16/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. fill the required input area 4.Write the first and last name with integers. 5. Observe that after pressing register button will redirect you to the login page. | Validation message that informs the user that only letters are allowed | After filling the required inputs and pressing the registration button it will redirect you to the login page as if it was a successful registration which is false because trying to login will fail because user registration wasn't saved to the database | Major | Habeeb Almseideen | Resolved
TC-DC-06 | Medium | When entering a new student data in the add student pop up if the processing of the save student wasn't successful the popup will close without any messages to inform the user that the data of the new student filled | /home | 18/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. Login 4.press add student button and fill the requierd inforomation 5.press save. | Validation messages that informs the user if there was any error | Popup window closes without saving the a new student data and without showing any error messages that caused the student data not to get saved | Major | Habeeb Almseideen | Resolved
TC-DC-07 | Low | Pressing the profile picture will open the edit profile layout behind the page | any page after Authentication | 20/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. Login 4.press profile photo . 5.Observe that the edit profile layout behind the page and cant be reached . | Being able to reach the edit profile button and log out button in the layout | not able to reach the edit profile button and log out button in the layout | Minor | Habeeb Almseideen | Resolved
TC-DC-08 | Low | in edit profile page when the change is successful, message successful position is not fixed as it supposed | /edit_profile | 25/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. Login 4.pressprofile photo . 5.press Edit Your profile button and change data then save and Observe that , message successful position is not fixed | show , message successful in a clear position where user will be informed that the prosses was successful | message successful position is showed after footer and not clear to observe | Minor | Habeeb Almseideen | Resolved
TC-DC-09 | Low | in home page the data table is showing the e-mail with a small horizontal column size | /home | 27/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. Login 4.observe thar the data table is showing the e-mail with a small horizontal column size | The column horizontal size must be fixed to a higher value where e-mail can be shown in one line | The column horizontal sizeis too small. | Minor | Habeeb Almseideen | Resolved
TC-DC-010 | Medium | In edit student data page and after pressing save the app will redirect you to the home page that shows that student data table without loading the data | /update_student/id | 27/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to the URL 3. Login 4.press Edit student button for any student and edit the requierd inforomation 5.press save and observe that student data table is not loading the data. | student data table must loading the data any time you open home page | student data table is not loading the data. | Major | Habeeb Almseideen | Resolved
TC-DC-11 | Low | When you're trying to enter to Any unregistered URL the error page 404 is not showing | any unregistered URL | 29/12/2023 | Mohammad Rawass | PC Windows 11 Google Crome (.6099) | 1. Open a new browser . 2. Navigate to ny unregistered URL 4.observe that 404 page not showing | 404 Error page not found page | 502 Error | Minor | Habeeb Almseideen | Resolved